Annex 2 Implementation Chart of the Twinning Project - Institutional Strengthening of the Environmental Health System of Georgia 


	 
	 
	 
	 
	 
	 
	 
	
	
	 
	 
	
	
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	No
	ACTIVITIES
	STE days
	1
	2
	3
	4
	5
	6
	7
	8
	9
	10
	11
	12
	13
	14
	15
	16
	17
	18
	19
	20
	21

	1
	RTA Installation
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	2
	0.1: Kick-off Conference
	6
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	3
	0.2: Closing conference
	6
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	4
	Project Reporting and Steering Committee Meetings
	21
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	5
	Activities for Result 1.Georgian legal and regulatory framework in environmental health field revised in-line with the provisions of the relevant Annexes of the Association Agreement related to the environmental health, as well as taking into account Georgia’s commitments towards Multilateral Environmental Agreements and other relevant international pledges (e.g. Parma Declaration);
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	 
	3.4.1.1 Assessment of legislative framework of Georgia in relation to environmental health field according to EU Directives and regulations 
	50
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	 
	3.4.1.2Develop proposal including recommendations for harmonisation of the Georgian legislation related to environmental health in compliance with EU requirements and other Environmental Agreements Directives 
	50
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	 
	3.4.1.3 Develop legal framework for establishment of environmental health system as a part of health system of Georgia 
	70
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	4
	Activities for Result 2. Institutional capacity of the Environment and Health Unit under the NCDC&PH strengthened
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	 
	3.4.2.1 Review of the structure and functions of the Environmental Health Division under the National Centre for Disease Control and Public Health
	20
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	 
	3.4.2.2 Drafting an Institutional Reform Plan for the Environmental Health Division under the National Centre for Disease Control and Public Health 
	25
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	 
	3.4.2.3 Gap Assessment of the Existing Environmental Health System
	25
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	 
	3.4.2.4 Mapping of functions of all stakeholders 
	25
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	 
	3.4.2.5 Elaboration of the procedures for the regular information exchange among responsible bodies 
	15
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	 
	3.4.2.6 Development of a communication strategy and awareness raising action plan
	30
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	 
	3.4.2.7 Study Visit to MS to be acquainted with the European Models of Environmental Systems in Practice  
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	5
	Activities for Result 3. Implementation of the National Environmental Health Action Plan (NEHAP) supported;
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	 
	3.4.3.1 Conduct Needs Assessment for implementation of NEHAP 
	20
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	 
	3.4.3.2 Training on tools and methodologies of costing 
	10
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	 
	3.4.3.3 Development of the Annual Action Plan (AAP) and its costing
	30
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	 
	3.4.3.4 Revision of NEHAP
	20
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	6
	Activities for Result 4. Capacities of Existing Environmental Health Human Resources, Including Management and Decision Makers Strengthened Along with Operationalization of Effective Environmental Health Management System in Compliance with EU Best Practices;
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	 
	3.4.4.1 Assessment  of the existing capacities of human resources in environmental health with all stakeholders
	25
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	 
	3.4.4.2 Develop scheme for Professional Development
	20
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	 
	3.4.4.3 Development of training programme and manual for environmental health human resources
	30
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	 
	3.4.4.4 Human Resources Training of the Environmental Health Division of NCDC&PH, regional centres and stakeholder institutions   
	50
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	 
	3.4.4.5 Conduct train-the-trainers course 
	15
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	 
	3.4.4.6 Internship for NCDC&PH Staff
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	 
	3.4.4.7 Study Visit to MS to get familiar with training systems 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	
	Total
	563
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	


2

